PEP PERFORMANCE REPORT

Flow Analysis  |  Data Pipeline Methodology

| Date: | 15 July 2026 |
| --- | --- |
| Project: | Global Events, Commodities and Currency Markets: Applied Data Analytics & Market Research |
| Prepared By: | Sandesh H. P. and Tharun |
| Report Period: | 01 June 2026 – 15 July 2026 |

# 1. Summary

This Performance Report summarizes the current status, progress, and key performance indicators (KPIs) for the project. The project leverages a Data Pipeline methodology to analyze Brent Oil, Gold and Silver, the SWIFT Tracker, and the USDG Stablecoin, alongside the current geopolitical conflict between the United States and Iran and the involvement of the BRICS bloc. The report covers project scope adherence, schedule, resource utilization, deliverables, risks, and other relevant areas.

# 2. Project Scope and Objectives

Scope

Analyze and compare global commodity, currency, and geopolitical event data using a Data Pipeline methodology.

Objectives

- Collect relevant data from reliable sources.

- Cleanse, transform, and integrate data into a standardized pipeline.

- Generate comparative analytics across commodities, currencies, and geopolitical variables.

- Deliver actionable insights for stakeholders.

# 3. Performance Analysis

A. Work Completed This Period

- Defined project roles and responsibilities.

- Finalized the Data Pipeline architecture.

- Extracted and cleaned data.

- Conducted preliminary comparative analysis.

- Drafted initial data visualizations (charts, tables).

B. Work Planned for Next Period

- Deepen analysis with geopolitical events and variables (e.g., value, volume, country-specific trends).

- Integrate supply chain traceability features into the pipeline.

- Prepare draft report and recommendations.

- Conduct stakeholder review and feedback sessions.

C. Key Accomplishments

- Established a repeatable, automated data extraction and transformation process.

- Identified major patterns and discrepancies in reported exports.

- Ensured data quality and traceability through pipeline checkpoints.

# 4. Schedule Performance

| Milestone | Planned Date | Actual Date | Status | Notes |
| --- | --- | --- | --- | --- |
| Project Kickoff | 01 June 2026 | 01 June 2026 | Completed | Project objectives, scope, datasets, and team responsibilities finalized. |
| Data Pipeline Design | 05 June 2026 | 05 June 2026 | Completed | Designed the data pipeline for data collection, preprocessing, and integration. |
| Data Extraction & Cleaning | 15 June 2026 | 15 June 2026 | Completed | Collected Brent Oil, Gold, Silver, SWIFT Tracker, and USDG datasets. Cleaned missing values, standardized formats, and prepared data for analysis. |
| Preliminary Analysis | 25 June 2026 | 26 June 2026 | Completed | Performed exploratory data analysis (EDA), generated descriptive statistics, and created initial visualizations to identify trends. |
| In-depth Analysis & Reporting | 08 July 2026 | 10 July 2026 | Completed | Conducted detailed analysis, interpreted findings, developed dashboards and charts, and prepared the final report with recommendations. |
| Final Report Submission | 15 July 2026 | 15 July 2026 | Completed | Submitted the complete report, presentation, supporting code, and project documentation. |

# 5. Budget and Resource Utilization

| Resource | Planned (hrs) | Actual (hrs) | Variance | Status / % |
| --- | --- | --- | --- | --- |
| Data Analysts | 80 | 82 | +2 hrs | Completed – 102.5% |
| Data Researchers | 60 | 58 | -2 hrs | Completed – 96.7% |
| Software Tools | 40 | 40 | 0 hrs | Completed – 100% |
| Total | 180 | 180 | 0 hrs | Completed – 100% |

# 6. Quality and Technical Performance

| Quality Indicator | Details |
| --- | --- |
| Data Accuracy | Achieved high data accuracy through data validation, removal of duplicates, handling missing values, and consistency checks during preprocessing. |
| Pipeline Uptime | The data pipeline operated reliably throughout the project, ensuring smooth data extraction, transformation, analysis, and visualization with no major interruptions. |
| Compliance | All data was collected from reliable public sources and handled in accordance with academic standards and data source requirements. |

# 7. Risks and Issues

| Risk / Issue | Status | Mitigation Action |
| --- | --- | --- |
| Data Gaps | Resolved | Missing values and incomplete records were identified during preprocessing and handled through data cleaning, validation, and appropriate imputation techniques. |
| Pipeline Integration Bugs | Resolved | The data pipeline was thoroughly tested, Python scripts were debugged, and each processing stage was verified to ensure smooth data flow. |
| Stakeholder Feedback Delays | Minor Impact | Regular team meetings and continuous communication ensured feedback was incorporated promptly without affecting the final project submission. |

# 8. Variance Analysis

| Area | Analysis |
| --- | --- |
| Schedule | The project was completed within the planned timeline. Minor delays during data analysis were effectively managed through task prioritization and teamwork, ensuring the final submission deadline was met. |
| Budget | The project remained within the planned resource allocation. Slight variations in effort between data analysis and research activities were balanced, resulting in no overall impact on project completion. |

# 9. Forecast

The project successfully established a reliable data pipeline for analyzing global commodities and currency market trends. Future enhancements may include integrating real-time data sources, expanding the range of financial indicators, and incorporating advanced machine learning models to improve predictive analytics. These improvements will provide more accurate insights and support better decision-making for business stakeholders.

# 10. Recommendations

- Integrate real-time APIs to enable continuous data collection and monitoring.

- Enhance the data pipeline by automating data validation and quality checks.

- Incorporate advanced predictive models to forecast commodity and currency market trends.

- Expand the analysis by including additional global economic indicators and geopolitical events.

- Regularly update datasets and dashboards to ensure timely and accurate business insights.

Authorizations

| Team Leader | Co-Team Leader |
| --- | --- |
| Signature: Name: Sandesh H. P. Date: 15 July 2026 | Signature: Name: Tharun Date: 15 July 2026 |

Prepared in accordance with standard PEP and performance reporting best practices.